## Slide 1: Wpromote KickOff Meeting
Authored by: Umang Dave Presented by: Umang Dave Date: 2/15/2013

## Slide 2: Agenda
Introduction
Project Scope
Tools & Technologies
Timeline
Communication Protocol / Reporting Mechanism
Deliverables
Challenges & Risks
Assumptions
Support Required
Questions
Next Step

## Slide 3: Introduction
Introduction to Client
Wpromote is a leading Online Marketing firm, providing services for Search Engine Optimization, PPC Management and Social Media.
Introduction to Project
The scope of this project focuses on the development and implementation of an Attribution and Reporting system that would help Wpromote and its customers derive insights into how their marketing and advertising campaigns are performing across multiple channels.

## Slide 4: Client Team Introduction
Michael Block – Chief Operating Officer
Jessica Como – Vice President of Client Services
Kevin Wallace – Director of Technology

## Slide 5: Cybage Team Introduction
Sr. Vice President, Practice Head – Media & Entertainment - Rajesh Kurup
Delivery Head Krudant Desai
Project Manager Umang Dave
Business Analyst Darshan Radia
Pratik Pandit
Sr Technical BA Sandeep Kulkarni
Developers Vishal Shukla (Tech Lead)
Rasulmiya Saiyad
Aakanksha Pant
UI Designer Rajesh Mishra
QA TBD

## Slide 6: Project Scope
Aggregating raw data from various sources
Analyzing, and processing advertising data
Implementing attribution and data logics
Implementing a front-end dashboard to access attribution reports and analytics
Implement Wpromote HTTP Handler and cookie tracker

## Slide 7: Tools & Technologies
Java 1.6 and J2EE
Pentaho Kettle
Apache Tomcat 7.0
Database Server (TBD)
Other Frameworks & Technologies (TBD)

## Slide 8: Timelines
8-Apr-13
Development environment setup, requirement understanding, design & POC development
Development of ETL, Data Aggregation, Dashboard & reports
12-Aug-13
5-Jul-13
Development of ETL, Data Aggregation, Dashboard & reports
27-May-13
System Testing/QA
These timelines may vary after the detailed project plan is created

## Slide 9: Responsibilities : Cybage
Activities to be completed by Cybage team
  Requirements Understanding
  UI design, development and integration
  Unit testing
  QA
List of items to be delivered by Cybage
  Deployable artifacts for aggregators, ETL components and web artifact for reporting & admin components

## Slide 10: Responsibilities: Client
User credentials for external data sources and APIs where applicable
Version control system credentials
Response to query within appropriate time
Subscribe to APIs/ data feeds and provide access to Cybage development team, for Wpromote accounts setup in system

## Slide 11: Communication Protocol
Call Timings and Schedule
  Frequency of calls
  Status calls
  Management sync-up calls
Point of Contact at each end
  Definition of who will participate within each call
Status reports
  Frequency of reports
  Format

## Slide 12: Escalation Mechanism
Threshold Period | Escalate to | Designation
<Issues raised by the Client> |  | 
< 3 days > | Umang Dave | Project Manager
< Above 7 days > | Krudant Desai | Delivery Manager
<Issues raised by Cybage> |  | 
< 3 days > | TBD | Project Manager
< Above 7 days > | Jessica Como / Kevin Wallace | VP, Client Services / Director, Software Engineering

## Slide 13: Challenges & Risk
Challenges Ahead
  Various third-party API integrations
  HTTP Handler and cookie tracker
Identified Risks
  The scope of the work is only defined at high level. Exploring the detailed requirements might lead to a scope change at later stage.

## Slide 14: Assumptions
Wpromote would provide user credentials for external data sources and APIs where applicable.
Wpromote would push the deployed application on the production environment after user acceptance testing (UAT) on the staging server. The Cybage team would assist in the deployment process.
Cybage has considered efforts for developing approx. 10 reports. Any additional reports would be implemented at additional efforts and cost.
Cybage’s recommended approach on custom cookie based tracking along with pixel tracking would require Wpromote to integrate a script on its advertisers websites / landing pages.
If the scope of work is changed, the timeline will be changed accordingly.

## Slide 15: Support Required
IS
TBD
HR
N/A
Training
Functional Training – Online Advertising
Admin
N/A

## Slide 16: Questions

## Slide 17: Next Step
Development Environment Setup
VPN or source code repository credentials
UI mock-ups

## Slide 18: Thank you.